## Project Portfolio
Project ID | Project Name | Manager | Status (RAG) | Start Date | End Date | Planned Cost ($M) | Actual Cost ($M) | Forecast Cost ($M) | Benefit Estimate ($M) | ROI (%)
P001 | Orion | A. Singh | Green | 2024-01-01 | 2024-12-31 | 5.5 | 3.1 | 5.6 | 8.5 | 55
P002 | Falcon | B. Patel | Amber | 2024-02-15 | 2024-11-30 | 6.2 | 4.9 | 6.5 | 10 | 61
P003 | Nebula | C. Roy | Green | 2024-03-01 | 2025-01-15 | 4.8 | 3.2 | 4.6 | 7.2 | 50
P004 | Atlas | D. Mehta | Red | 2024-01-20 | 2024-12-15 | 5 | 4.8 | 6.2 | 9 | 45
P005 | Zephyr | E. Rao | Amber | 2024-04-01 | 2025-03-30 | 3.9 | 2.9 | 4.1 | 6 | 54

## Resource Allocation
Resource ID | Name | Role | Project Assigned | Planned Hours | Actual Hours | Availability (%) | Cost Rate ($/hr)
R101 | J. Kumar | BA | Orion | 1200 | 900 | 100 | 50
R102 | T. Ali | Dev | Falcon | 1400 | 1100 | 100 | 60
R103 | S. Verma | QA | Nebula | 1000 | 850 | 80 | 40
R104 | L. Gupta | PM | Atlas | 1600 | 1350 | 100 | 80
R105 | M. Das | UX | Zephyr | 800 | 750 | 60 | 45

## RAID Log
Item ID | Type | Description | Owner | Impact | Probability | Status | Mitigation Plan | Target Date
RSK001 | Risk | Vendor delivery may be delayed due to contract changes | PM | High | Medium | Open | Add buffer; discuss alternate vendor | 2024-08-01
ISS002 | Issue | Environment not stable for testing | QA Lead | Medium | High | Open | Weekly stability reviews with infra | 2024-07-15
DEP003 | Dependency | Dependent on external API upgrade | Integration Lead | High | High | Open | Align timeline with vendor commitment | 2024-09-01
ASS004 | Assumption | Budget approval assumed for Q3 expansion | Finance Controller | Low | Low | Logged | Track approvals with Finance biweekly | 2024-07-30

## Timesheet Logs
Resource Name | Project | Week Ending | Total Hours | Comments
J. Kumar | Orion | 2024-06-30 | 40 | Worked on requirements; waiting for stakeholder review
T. Ali | Falcon | 2024-06-30 | 38 | Dev completed, blocked by code review
S. Verma | Nebula | 2024-06-30 | 36 | Test plan completed, few test cases pending
L. Gupta | Atlas | 2024-06-30 | 42 | Steering committee postponed; need inputs
M. Das | Zephyr | 2024-06-30 | 34 | Some rework due to design change